## Sheet1
List of SPC Playground Equipment
Fletchers Croft | Issue | Risk | Actions required following June 2021 Wicksteed Inspection | Action still to be completed since inspection | manufacturer
Chair Spinner | loose in foundation | Moderate | Reinstall item to secure. Manufacturer contacted and quote agreed for works to be completed (under guarantee) - Due on site 7th October | Works to be completed on the 7th October - the contractors earliest availability - Now 3rd Nov. due to Covid- Has been taken out of service to allow playground re-opening | Creative play
See Saw | Fixings Loose | Moderate | SPC Contractor has Checked & Tightened | Completed | Creative play
Rocking dog | Handgrip/foot rest loose & Fixings Missing | Moderate | SPC Contractor has Checked & Tightened | This then to be checked by Creative play engineer as still some movement | Creative play
Surface/grass | trip hazards | Moderate | Top soil to be added to uneven grassed areas | Grass uneveness works Completed | Creative play
Multi Play bridge | Rough/splintered timber | Low | Rub Back or replace to be completed | To be completed week beginning 7th October - Now by 3rd November due to engineers having Covid | Creative play
Rocking Duck | Handgrip/foot grip rotate and loose fixings | Moderate | SPC Contractor has Checked & Tightened | This then to be checked by Creative play engineer as still some movement | Creative play
Wet Pour | Gaps in surface | low | Wet pour kits have been purchased to complete crack repairs | Gaps to be monitored as have shrunk due to weather | Creative play
Litter Bin | Bin Liner loose | low | SPC Contractor to put bolt liner back on - Ground fixing recommended ?? | Completed | Creative play
Picnic tables | fire damage | Low | Contractor to continue to monitor |  | SPC
Gate | Gap less the 12mm | Low | Contractor to look and inform if he can remidy | To be completed by SPC Contractor | Wicksteed
1 Bay 2 swings (Cradle) | bolt caps missing | very low | Replacement caps ordered - To be remedied when caps arrive by contractor | Completed | Creative play
1 bay 2 swings (flat) | bolt caps missing | very Low | Replacement caps ordered - To be remedied when caps arrive by contractor | Completed | Creative play
Train | None | very low | None |  | Creative play
play panel | None | Very Low | None |  | Creative play
Train | None | very low | None |  | Creative play
Bench | None | Very Low | none |  | SPC
Fence | None | very low | None |  | SPC
sign | None | Very low | None |  | SPC
Memorial Playing Field | issue | risk | Actions required following June 2021 Wicksteed Inspection | Action still to be completed since inspection | manufacturer
Over Head Rotator | Surface damaged | Moderate | Wet pour kits have been purchased to complete crack and hole repairs - Repair kits have been delivered - Cracks to be repaired week beginning 6th September | Completed | Wicksteed
1 bay 2 swings (flat) | loose fixings on top bar | Moderate | 1 swing tightened and 1 removed as unable to tighten and was too loose to leave in play. New fixings to be purchased when back in stock | To be completed - awaiting new brackets to come in stock …...........Brackets arrived 27th Oct. | unknown
Rotating net | Surface damaged | Moderate | Wet pour kits have been purchased to complete crack and hole repairs | Cracks and holes repaired - Tape to repair reinforced also used WORK COMPLETED | Wicksteed
Basket swing | basket swing removed | Moderate | Manufacturer to replace Basket Swing (on 17th August) | Completed - New equipment installed | Creative Play
Rocking & Cross equipment | Surface is danaged around the item | Moderate | SPC Contractor is investigating wet pour kits to purchase and complete repairs | Completed | Big Toys
Gates to park | Surface is danaged | Moderate | Contractor to build up earth ands secure rubber mats in place and grass seed them | Completed | wicksteeds
Bench seats | rotted timber | Moderate | Contractor to replace affected timbers | Completed | SPC
Parallel Bars | loose fixings and erroded ground surface | Moderate | Contractor to tighten - and to re turf ground | Partially Completed - more ground works and soil required | Fawns Recreational services
1 bay 2 swings (Cradle) | Surface is damaged around the item | Low | Contractor is investigating wet pour kits to purchase | Surface repaired but seat has been removed as seats are perishing - parts arrived on 27th Oct. | big Toys
Somersault bars | Surface is damaged around the item | Low | Contractor can re turf or put down mats and grass seed | To be completed | wicksteed
Balance beam | Surface is damaged around the item | Low | Contractor can re-turf | To be completed | wicksteed
Slide Unit | Rope nets are worn Graffiti requires removing | Low | Contractor to monitor nets Caretaker to remove graffiti if possible - Done | To be completed | unknown
Multi play | None | Very Low | None |  | wicksteed
Boulders | None | Very Low | None |  | unknown
Fence | None | Very Low | None | Some Gravel boards, rails and mesh are being replaced - noted by contractor during monthly checks | SPC
Shelter | None | Very Low | None |  | Wicksteed
Bolders | None | Very Low | None |  | Unknown
Spinning Pole | None | Very Low | None |  | Wicksteed
Low Walk | None | Very Low | None |  | Unknown
Litter Bin | Nine | Very Low | None |  | SPC
Chandlers Way | issue | risk | Actions required following June 2021 Wicksteed Inspection | Action still to be completed since inspection | manufacturer
1 Bay 2 swings (cradle and flat) | bushes are worn or missing | Moderate | Replacment items to be purchased / works to be completed by SPC contractor | Done | unknown
Slide | loose in foundation | Moderate | reinstall item to make secure / Manufacturer | Slide removed from site and ground made good - Complteed | unknown
Fence | loose slats | Moderate | Repair as required | Done | spc
Gate | Timber rough and splintered | low | Contractor can Rub down or replace gate | Done | SPC
Benches | Timber rough and splintered | low | Contractor can Rub down but needs replacing | To be completed | SPC
Waste bin | split | low | Need to replace bin | To be completed | SPC
Gate | Gap wider that 12mm | low | contractor to continue to check and adjust as necessary |  | SPC
Hedge | overgrown vegetation | low | To be done | DONE | SPC
Sign on gate | None | very low | Sign is now on gate
South Ash | issue | risk | Actions required following June 2021 Wicksteed Inspection | Action still to be completed since inspection | manufacturer
Path way surface | tarmac is cracking | low | Contractor to do tarmac reapairs with cold tar and remove weeds | Done | unknown
Multi Play | gaps between surface tiles | low | Contractor can take up tiles, clean and replace them | Partially done | unknown
fence/ground surface | overgrown vegetation | low | weed and cut back - To be completed by id verde contractor - ASAP - when access available | Done | unknown
1 bay 2 swings | Worn seat & chains | Low | will need to replace seats and chains when they get to 40% worn | To be completed by SPC contractor - will be monitored | unknown
Bench seat | None | Very low | none |  | SPC
Fence Bow Top | none | Very low | none |  | unknown
Fence Timber | None | Very low | none |  | Spc and ajoining land owner
Gate | None | Very low | none |  | unknown
sign | None | Very low | none |  | spc
Abbey Road | issue | risk | Actions required following June 2021 Wicksteed Inspection | Action still to be completed since inspection | manufacturer
Pathway | Cracked tarmac | Moderate | Contractor to do tarmac repairs with cold tar | Cracked Tarmac repairs to path completed | unknown
Safety surface tiles | gaps in between the tiles | low | Contractor can take up tiles, clean and relay the tiles | To be completed by SPC contractor | unknown
1 bay 1 swing | Chain Wear and seat with long screws | Moderate | Contractor to monitor chains and to cut off exposed threads of nuts | Exposed threads cut off - thereby reducing risk - chains to be continued to be monitored | unknown
bin | none | very low | none |  | HDC
Bench | none | very low | none |  | spc
fence | none | very low | none |  | unknown
gate | none | very low | none |  | unknown
Multi play | none | very low | none |  | unknown
Hedges/bushes | overgrown | very low | Cutting back - DONE
.